## 1
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Sprint | 1
Explorer View | Create Firebase Database | 3 | 3 | 1 | 2 | Leeb | Von | 2020-02-24
Explorer View | Create Repositories which use Firebase | 4 | 4 |  | 4 | Leeb | Bis | 2020-03-09
Explorer View | Provide Image for guide | 4 | 4 | 2 | 2 | Wirth
Explorer View | Cors configurieren | 2 | 3 | 3 | 0 | Wirth, Engleder
Explorer View | Data Initializer (InMemory) | 2 | 1 | 1 | 0 | Wirth
Explorer View | Guide Information Page | 2 | 2 | 2 | 0 | Quoc, Engleder
Explorer View | Create Models at the serverside | 2 | 1 | 1 | 0 | Wirth
Explorer View | Create a Data Initializer on the server | 3 | 3 | 0 | 3
Explorer View | Support Rest service at the serverside (for guides) | 3 | 2 | 2 | 0 | Wirth
Explorer View | Get Image of guide from Server | 4 | 1 | 1 | 0 | Wirth, Leeb
Explorer View | Get guides from server | 1 | 1 | 1 | 0 | Engleder, Quoc
Explorer View | Display guides on explorer view | 2 | 2 | 2 | 0
Explorer View | Cors Problem | 4 | 1 | 1 | 0
Explorer View | Information Page | 3 | 4 | 3 | 1 | Engleder
Explorer View | Routes for Explorer View (server) | 3 | 3 | 2 | 1 | Wirth, Leeb
Explorer View | Image Provider (Dynamischer Pfad) | 2 | 1 | 1 | 0 | Wirth
Explorer View | Create Repositories which use Firebase | 4 | 4 | 4 | 0 | Leeb
Registration | Storing User in DB (Server) | 2 | 2 | 0 | 2
Registation | Send Confirmation Mail on registration (Server) | 3 | 3 |  | 3
Login | Login Routing | 2 | 2 | 2 | 0 | Quoc
Explorer View | Infinite Scroll | 2 | 2 | 2 | 0 | Quoc
Explorer View | Get guides from Server | 1 | 1 | 1 | 0 | Quoc
32

## 2
[7 empty] | Sprint | 2
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2020-03-09
[7 empty] | Bis | 2020-03-23
Explorer View | Routes for Explorer View (server) | 1 | 1 |  | 1 | Wirth, Leeb
Explorer View | Create Repositories which use Firebase | 1 | 3 | 2 | 1 | Leeb
Explorer View | Manage Users (Create and Read - server) | 3 | 3 | 2 | 1 | Leeb
Explorer View | Test Daten machen (server) | 1 | 1 | 1 | 0 | Wirth
Registration | Storing User in DB (Server) after clicking on confirm | 2 | 2 |  | 2
Registation | Send Confirmation Mail on registration (Server) | 3 | 5 | 4 | 1 | Wirth
Explorer View | Information Page | 2 | 3 | 3 | 0 | Engleder
Registration | Registration GUI | 3 | 3 | 2 | 1 | Engleder
Registration | Registration Logic | 2 | 2 |  | 2
Login | Login GUI | 3 | 3 | 3 | 0 | Quoc
Login | Login Logic | 3 | 2 | 2 | 0 | Quoc
0
|  |  | 0 | 19

## 3
[7 empty] | Sprint | 3
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2020-03-23
Registration | Sending Email on registration Verification | 3 | 3 | 2 | 1 | Leeb | Bis | 2020-04-06
Registraion | Add User to Firebase, when clicking on verification link | 2 | 2 |  | 2 | Wirth
Login | Check if user is registered in the DB | 3 | 3 |  | 3 | Leeb
Login | Send Token to client for further methods | 3 | 3 |  | 3 | Wirth
Registration | User Repository | 2 | 1 | 1 | 0 | Leeb
Registration | Create Repositories which use Firebase | 1 | 1 | 1 | 0 | Leeb
Registration | Endpoint fixes | 1 | 1 | 1 | 0 | Wirth
Registration | Filter guides | 3 | 5 | 4 | 1 | Wirth
Registration | Create Endpoints for DB-Reads | 2 | 2 | 2 | 0 | Leeb
Profile | Profile UI | 4 | 4 | 4 | 0 | Quoc
Home | Slider configuration | 1 | 1 | 1 | 0 | Quoc
|  |  | 0 |  | 0
Explorer View | Information Page | 2 | 3 | 3 | 0 | Engleder
Registration | Registration GUI | 3 | 2 | 2 | 0 | Engleder
LoginLogic Firebase |  | 4 | 4 | 3 | 1
Login Validation |  | 3 | 5 | 3 | 2
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
27

## 4
[7 empty] | Sprint | 4
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2020-04-20
Registration | Authentication | 4 | 2 | 2 | 0 | Wirth | Bis | 2020-05-04
Registration | Endpoint Testing | 3 | 3 | 3 | 0 | Leeb
Registration | Refactoring | 2 | 2 | 2 | 0 | Wirth
|  |  | 0 |  | 0
General | Route Logging (with morgan?) | 2 | 1 | 1 | 0 | Wirth
General | Debug Logging | 3 | 0.5 | 0.5 | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
Login | Authentication | 1 | 2 | 2 | 0 | Quoc
Create Guide | Guide Creation UI | 6 | 6 | 2 | 4
Login | Login and Registration Validation | 1 | 2 | 2 | 0
Login | Login With Google | 2 | 2 | 2 | 0
|  | 24 |  | 16.5

## 5
[7 empty] | Sprint | 5
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2020-05-04
[7 empty] | Bis | 2020-05-18
Profile | Sorting and Filter of Ratings | 3 | 3 |  | 3
Create Guide | Other Parts of Server Logic | 2 | 2 |  | 2
Create Guide | Add Guide through Endpoint | 1 | 0.5 | 0.5 | 0 | Leeb, Wirth
General | Optimize Logging Features | 2 | 0.5 | 0.5 | 0 | Wirth
General | Bug Fixes | 2 | 2.5 | 2.5 | 0 | Leeb, Wirth
Create Guide | Body Parser (Middleware) | 1 | 1 | 1 | 0 | Wirth, Leeb
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
Login | Fixed Routing issues | 1 | 2 | 2 | 0 | Quoc
Secure Data Transfer | JWT | 2 | 4 | 4 | 0 | Quoc
Create Guide | Guide Creation UI (with chronologicalOption) | 6 | 4 | 2 | 2 | Engleder
Create Guide | Guide Creation Logic with Server | 3 | 3 | 1 | 2 | Engleder
Create Guide | Frontend Porting to Website | 5 | 5 | 3 | 2
|  |  | 0 |  | 0
Manage Guide |  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
0
0
|  |  | 27.5 | 16.5

## 6
[7 empty] | Sprint | 6
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2020-05-18
[7 empty] | Bis | 2020-06-01
User Management | Add User through endpoints | 2 | 3 | 3 | 0 | Leeb
Profile | Sorting and Filter of Ratings | 2 | 4 | 4 | 0 | Wirth
Create Guide | Add nearest track or first track flag | 1 | 1 | 1 | 0 | Leeb
General | Fancy ASCII Art Title | 1 | 1 | 1 | 0 | Wirth
Secure Data Transfer | Decrypt Messages sent by the client | 2 | 2 |  | 2 | Wirth, Leeb
Create Guide | Add Chronological-Flag | 1 | 1 | 1 | 0 | Leeb
|  |  | 0 |  | 0
Secure Data Transfer | HTTP Interceptors | 3 | 3 | 3 | 0 | Quoc
Secure Data Transfer | HTTP Requests | 2 | 2 | 2 | 0 | Quoc
Secure Data Transfer | AuthGuard | 3 | 3 | 3 | 0 | Quoc
Create Guide | Guide Creation UI (with chronologicalOption) | 6 | 6 | 4 | 2 | Engleder
Create Guide | Guide Creation Logic with Server | 3 | 3 | 1 | 2 | Engleder
Create Guide | Frontend Porting to Website | 5 | 6 | 6 | 0 | Engleder
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
0
|  | 31 | 35 | 29

## 7
[7 empty] | Sprint | 7
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2020-06-01
[7 empty] | Bis | 2020-06-15
Guide Creation | Image Upload Manager | 3 | 3 | 2.5 | 0.5 | Wirth
Secure Data Trandf. | Https Connection at the backend | 3 | 0.5 | 0.5 | 0 | Wirth
General | Error Handling in Endpoints | 3 | 1.5 | 1.5 | 0 | Wirth
Manage Tracks | Track Upload Manager | 3 | 5 | 5 | 0 | Leeb
Create Guide | Tag filtering (Top Used, Beginning with Letter) | 2 | 2 | 2 | 0 | Wirth
Create Guide | Update Field numberofUses in Tag when adding or updating a guide | 2 | 2 |  | 2
Profile | Add imageQuoch to profile picture of the user | 1 | 1 | 1 | 0 | Wirth
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
Create Guide | Guide Creation UI | 6 | 8 | 8 | 0 | Engleder
Create Guide | Guide Creation Logic with Server | 3 | 5 | 5 | 0 | Engleder
Secure Data Transfer | HTTPS | 2 | 2 | 2 | 0 | Quoc
Secure Data Transfer | Fixed CORS | 1 | 2 | 2 | 0 | Quoc
General | Fixed HTTP requests for images | 0.5 | 1 | 1 | 0 | Quoc
Gmaps JS API | First Time Integration | 2 | 1 | 1 | 0 | Engleder
Secure Data Transfer | Logout | 0.5 | 0.5 | 0.5 | 0 | Quoc
General | Create User Request | 1 | 1 | 1 | 0 | Engleder
Explorer View | Sort | 1 | 1 | 1 | 0 | Engleder
Create Guide | Improve image import | 2 | 2 | 2 | 0 | Quoc
General | Resolving signup issues | 1 | 2 | 2 | 0 | Quoc
|  |  | 0 |  | 0
|  | 37 | 40.5 | 38

## 8
[7 empty] | Sprint | 8
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2020-06-15
[7 empty] | Bis | 2020-06-29
Manage Tracks | (Audio)Track-Upload | 4 | 4 | 3 | 1 | Leeb
General | Refactoring um Wartbarkeit zu erhöhen | 3 | 3 | 3 | 0 | Lukas
Create Guide | Tags are added to DB on Guide Creation or Update | 2 | 2 | 2 | 0 | Lukas
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0 |  | 5 Min Präsentation, Wos geht wos is,momentaner Stand, fehlende User Stories, geplanter Fertigtermin (Burndown - ca. 1.März)
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
Create Guide | Cropping pictures | 4 | 6 | 4 | 2 | Engleder
Create Guide | Track Management | 6 | 6 | 2 | 4 | Engleder
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | 19 | 21 | 14

## 9
[7 empty] | Sprint | 9
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2020-09-19
[7 empty] | Bis | 2020-10-02
| Refactoring Server | 3 | 3 | 2 | 1 | Lukas
GMA02 | Track Endpoint | 3 | 3 | 3 | 0 | Leeb
| Refactor to MongoDB | 9 | 8 | 6 | 2 | Lukas
GMA02 | Add trackName and trackLength to response | 2 | 2 | 2 | 0 | Leeb | General
| Refractor Defined Changes | 3 | 3 | 1 | 2 | Leeb | Lukas Wirth
|  |  | 0 |  | 0 |  | Leeb Leeb
|  |  | 0 |  | 0 |  | Quoc
|  |  | 0 |  | 0 |  | Engleder
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
General | Fix issue with Ionic | 1 | 3 | 3 | 0 | Quoc
General | Upgraded to Ionic 5 | 2 | 2 | 2 | 0 | Engleder, Quoc
LAG01 | Initial setup | 0.5 | 0.5 | 0.5 | 0 | Quoc
LAG01 | Implement Streaming API | 2 | 2 |  | 2
GMA02 | Map Taggin (Modal) with Track | 3 | 3 | 2 | 1 | Engleder
GMA02 | Upload Track | 2 | 2 | 0 | 2 | Engleder
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Soll | 30.5 | 24 | 21.5
| Haben |  | 14
Refactor:
| TrackDB => Tracks, Track => TrackFIles | x
CreateNewGuide Rest Route => returns GuideID
| imageUpload, trackUpload (username, guideId) | x

## 10
[7 empty] | Sprint | 10
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2020-10-02
[7 empty] | Bis | 2020-10-16
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Finish Endpoint Validations | 2 | 2 | 1 | 1 | Wirth
| Refactoring Database to MongoDb | 3 | 3 | 2 | 1 | Wirth | General
| Refractor Defined Changes | 2 | 3 | 3 | 0 | Leeb | Lukas Wirth
| Test refactorChanges | 1 | 1 | 1 | 0 | Leeb | Leeb Leeb
| Streaming with howler.js | 2 | 2 | 2 | 0 | Quoc | Quoc
| Streaming UI Concept | 2 | 2 | 2 | 0 | Engleder. Quoc | Engleder
| Streaming Logic | 1 | 1 | 1 | 0 | Quoc
| Spike Beacons | 1 | 2 | 1 | 1 | Engleder
| Testing streaming with mock data | 0.5 | 0.5 | 0.5 | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Mapbox Integration | 3 | 3 | 3 | 0
| On Click show Guide Overlay | 2 | 2 | 2 | 0
| On Click show Track Overlay | 2 | 2 | 2 | 0
| Pin Locations On Map | 2 | 1 | 1 | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Soll | 23.5 | 0 | 21.5
| Haben |  | 24.5
Refactor:
| TrackDB => Tracks, Track => TrackFIles | x
| CreateNewGuide Rest Route => returns GuideID | x
| imageUpload, trackUpload (username, guideId) | x
| Trackname (Trackmodel) | x
Sysadmin Server Rennen

## 11
[7 empty] | Sprint | 11
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2020-10-16
[7 empty] | Bis | 2020-11-06
| Refactor: Docker server | 6 | 5 | 5 | 0 | Wirth
| Added Mapping to Track Datastructure | 5 | 5 | 5 | 0
0
[5 empty] | 0 |  | General
[5 empty] | 0 |  | Lukas Wirth
[5 empty] | 0 |  | Leeb Leeb
[5 empty] | 0 |  | Quoc
| Refactor Guide Creation | 2 | 2 | 2 | 0 |  | Engleder
| Docker Frontend | 4 | 4 | 4 | 0 |  | Engleder
| Upload Track with Location Mapping | 2 | 3 | 3 | 0 |  | Engleder
| Added About Page | 1 | 1 | 1 | 0 |  | Engleder
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Soll | 20 | 0 | 20
| Haben |  | 20

## 12
[7 empty] | Sprint | 12
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2020-11-06
[7 empty] | Bis | 2020-11-20
| Deployment: Server image auf der Vm | 2 | 2 | 2 | 0 | Wirth
| Refactor: Error fixing | 3 | 3 | 3 | 0 | Wirth
|  |  | 0 |  | 0
| GetTracks in Vicinity of User (5km, N: 30) | 5 | 5 | 3 | 2 | Leeb
| Filtering of Guides in Vicinity of User |  | 0 |  | 0
| Mongodb Track Repository | 4 | 4 | 4 | 0 | Leeb
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Refactored UX Guide Creation on Web | 2 | 2 | 2 | 0 | Engleder
| Added Explorer View to Web | 3 | 3 | 3 | 0 | Engleder
| Tried to add LetsEncrypt to server (solved by traefik) | 2 | 2 | 2 | 0 | Engleder
| Stay logged In feature with FireAuth | 2 | 4 | 4 | 0 | Quoc
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Discussion about tracks | 8 | 8 | 8 | 0 | Team
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Soll | 31 | 0 | 31
| Haben |  | 33

## 13
[7 empty] | Sprint | 13
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2020-11-20
[7 empty] | Bis | 2020-12-04
| Traefik Configuration | 5 | 7 | 7 | 0 | Wirth
| Bug fixing | 5 | 6 | 6 | 0 | Wirth
|  |  | 0 |  | 6
| GetTracks in Vicinity of User (5km, N: 30) | 4 | 4 | 4 | 0 | Leeb
| Check for available Track of Guide with given Position |  |  |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Added Personal Guides to profile | 2 | 2 | 2 | 0 | Quoc
| Fixed Google Signin Bug | 2 | 2 | 2 | 0 | Quoc
| Added Logout Button, Refactored Auth | 1 | 1 | 1 | 0 | Quoc
| Guide Pins auf Map | 4 | 4 | 4 | 0 | Quoc
| Refactor Guide Information View | 2 | 2 | 2 | 0 | Quoc
| Keep Logged In after refresh | 1 | 2 | 2 | 0 | Wirth
| Skript für Tracks verfassen + feedback geben | 16 | 16 | 16 | 0 | Team
|  |  | 0 |  | 0
| Track Pins auf Map (brauche noch GuideId) | 3 | 3 | 3 | 0 | Engleder
| Added Track Detail View | 2 | 2 | 2 | 0 | Engleder
| Listen to Tracks | 2 | 2 | 2 | 0 | Engleder
| Login/Signup Animation | 2 | 2 | 2 | 0 | Engleder
| Fixed Validation | 1 | 1 | 1 | 0 | Engleder
|  |  | 0 |  | 0
| Manage Guides (Delete...) | 2 | 4 | 2 | 2 | Leeb
| GetGuidesByLocation | 4 | 6 | 6 | 0 | Leeb, Engleder
| Private/Public (Post, und GetGuides) | 2 | 2 | 2 | 0 | Leeb
Authorization (Admin Account)
|  |  | 0 |  | 0
| Soll | 60 |  | 66
| Haben |  | 56

## 14
[7 empty] | Sprint | 14
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2020-12-04
|  |  | 0 |  |  |  | Bis | 2020-12-18
| Manage Guides (Delete...) | 3 | 3 | 3 | 0 | Leeb
| Filter Guides (popularity, tags, rating) with Location | 2 | 4 | 1 | 3 | Leeb
| Angabe des Radius bei getByLocation | 1 | 1 | 1 | 0 | Leeb
| Hidden tracks ¦ backend | 0.5 | 0.5 | 0.5 | 0 | Leeb
| Get Guide by Id | 0.5 | 0.5 | 0.5 | 0 | Leeb
0
| Display Radius on Guide Creation/(Main Map) |  | 0 |  | 0
| Tab Bar | 3 | 4 | 4 | 0 | Engleder
| Star Button Size Change | 1 | 1 | 0 | 1
| Try, update and fix cordova-geofence-plugin | 3 | 6 | 5 | 1 | Engleder
| Migrate to Capacitor | 3 | 3 | 3 | 0 | Engleder
|  |  | 0 |  | 0
| HTTPS Connection Frontend | 2 | 2 | 2 | 0 | Wirth
| Geo Fence Prototype | 3 | 3 | 3 | 0 | Wirth
| Pwa in Traefik link | 2 | 7 | 7 | 0 | Wirth
| Streaming UI | 3 | 3 | 3 | 0 | Quoc
| Streaming Logic | 3 | 3 | 3 | 0 | Quoc
| Fix Google SignIn on Mobile | 2 | 4 | 4 | 0 | Quoc
| Building signed APK | 0.5 | 0.5 | 0.5 | 0 | Quoc
|  |  | 0 |  | 0
| Meeting Bauer | 2 | 2 | 2 | 0 | Engleder, Quoc, Wirth
0
|  |  | 0 |  | 0
| Soll | 34.5 |  | 42.5
| Haben |  | 45.5

## 15
[7 empty] | Sprint | 15
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2020-12-18
| GetByLocation return Tracks ordered (by current location) (Backend) | 3 | 3 | 3 | 0 | Leeb | Bis | 2021-01-08
| Guide Creation Save Order of tracks (Backend) | 2 | 2 | 2 | 0 | Leeb
|  |  | 0 |  | 0
0
| treafik pwa route | 10 | 10 | 10 | 0 | Wirth
0
0
|  |  | 0 |  | 0
| Debug and Test cordova-background-geolocation | 5 | 5 | 5 | 0 | Quoc
| Implement Background Location | 3 | 5 | 5 | 0 | Engleder
|  |  | 0 | 0
| Write Schauflinger Tracks | 2 | 2 | 2 | 0 | Engleder
|  |  | 0 | 0 | 0
| Tooltip | 3 | 3 | 3 |  | Engleder
| Guide Editing | 4 | 4 | 4 | 0 | Engleder
| Track Editing (Only Name and File) | 3 | 3 | 3 | 0 | Engleder
|  |  | 0 |  | 0
| Meeting Bucek & Schröder | 3 | 3 | 3 | 0 | Engleder, Quoc, Leeb, Wirth
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
0
|  |  | 0 |  | 0
| Soll | 38 |  | 40
| Haben |  | 37

## 16
[7 empty] | Sprint | 16
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2021-01-08
| GetByLocation return Tracks ordered (by current location) (Backend) | 2 | 2 | 2 | 0 | Leeb | Bis | 2021-01-22
| Guide Creation Save Order of tracks (Backend) | 2 | 2 | 2 | 0 | Leeb
| Save Logs in File | 1.5 | 1.5 | 1.5 | 0 | Leeb
| Download Button on Android Web | 2 | 2 | 2 | 0 | Engleder
| Dark Mode | 2 | 2 | 2 | 0 | Engleder
| Make Preferences Page | 2 | 2 | 2 | 0 | Engleder
| Storage Management | 3 | 3 | 3 | 0 | Engleder
|  |  | 0 |  | 0
0
| Click on Guide => Fitbounds + Zoom | 3 | 2 | 2 | 0 | Engleder
| Preference Backgroundmode | 1 | 1 | 1 | 0 | Quoc
| On mobile devices, redirect to PWA | 3 | 3 | 3 | 0 | Quoc
| Background Location Fixes | 2 | 2 | 2 | 0 | Engleder
0
| Meeting Bucek & Schröder | 4 | 4 | 4 | 0 | Engleder, Quoc, Leeb, Wirth
|  |  | 0 |  | 0
| VM Infrastructure | 6 | 6 | 6 | 0 | Wirth
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
0
|  |  | 0 |  | 0
| Soll | 33.5 |  | 32.5
| Haben |  | 30.5

## 17
[7 empty] | Sprint | 17
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2021-01-22
|  |  | 0 |  | 0 |  | Bis | 2021-02-05
| Profile Picture Management im Backend | 3 | 3 | 3 | 0 | Wirth
| User Edit Routes im Backend | 2 | 2 | 2 | 0 | Wirth
| Add User Description | 1 | 1 | 1 | 0 | Wirth
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| QR Code- & Number-Mapping (backend) | 2 | 4 | 2 | 2 | Leeb
| Secure Track and Guide-Update | 2 | 2 | 2 | 0 | Leeb
| Add username to GetNearGuidesCall | 1 | 1 | 1 | 0 | Leeb
|  |  | 0 |  | 0
| Reset Password UI | 2 | 2 | 2 | 0 | Engleder
| Guide Page Link | 3 | 2 | 2 | 0 | Engleder
| Redirect URL | 3 | 3 | 3 | 0 | Engleder
|  |  | 0 |  | 0
| Fix track player with multiple tracks issue | 3 | 4 | 4 | 0 | Engleder, Quoc
| Android Back Button | 2 | 2 | 2 | 0 | Quoc
| Profile Edit Web prototyp | 4 | 4 | 4 | 0 | Quoc
| Profile View (Mobile) prototype | 4 | 5 | 5 | 0 | Quoc
| StorageFix | 1 | 1 | 1 | 0 | Quoc
| Version Check + Download | 4 | 5 | 5 |  | Engleder
| Safari Fix: flex - gap to margin | 2 | 2 | 2 |  | Engleder
0
0
0
| Pictures in about | 1 | 1 | 1 |  | Engleder
| Meeting Bucek & Schröder | 4 | 4 | 4 | 0 | Engleder, Quoc, Leeb, Wirth
| Soll | 40 |  | 41
| Haben |  | 41
0
Error Messages Verbessern

## 18
[7 empty] | Sprint | 18
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2021-02-05
|  |  | 0 |  | 0 |  | Bis | 2021-02-26
| QR Code- & Number-Mapping (backend) | 3 | 3 | 3 | 0 | Leeb
| Update Track routes | 4 | 4 | 4 | 0 | Leeb
|  |  | 0 |  | 0
| Frontend refactor | 8 | 8 | 8 | 0 | Wirth
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Track only plays once | 3 | 3 | 3 | 0 | Engleder
| Display Track is playing/disabled | 4 | 4 | 4 | 0 | Engleder
| Fix Background Mode Bug | 2 | 2 | 2 | 0 | Engleder
| Fix Streaming error | 3 | 3 | 3 | 0 | Quoc
| Track Player Route fixed | 2 | 4 | 4 | 0 | Quoc
| Landing Page Design | 6 | 6 | 6 | 0 | Engleder
|  |  | 0 |  | 0
| Meeting Bucek & Schröder | 3.5 | 3.5 | 3.5 | 0 | Engleder, Quoc, Leeb, Wirth
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Soll | 38.5 |  | 40.5
| Haben |  | 40.5

## 19
[7 empty] | Sprint | 19
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2021-02-26
|  |  | 0 |  | 0 |  | Bis | 2021-03-12
| Secure User-Update | 2 | 2 | 0 | 2 | Leeb
|  |  | 0 |  | 0
| Refactor Frontend | 6 | 6 | 6 | 0 | Wirth
| Vm Infrastructure | 3 | 3 | 3 | 0 | Wirth
|  |  | 0 |  | 0
| Landing Home Page (Design + Implementation) | 9 | 10 | 8 | 2 | Engleder
|  |  | 0 |  | 0
| Trackqueue | 4 | 4 | 4 | 0 | Engleder
| Landing Page - App & Download | 7 | 7 | 7 | 0 | Engleder
| Profile Hub | 2 | 2 | 2 | 0
|  |  | 0 |  | 0
| Meeting Bucek & Schröder | 6 | 6 | 6 | 0 | Engleder, Quoc, Leeb, Wirth
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
0
0
0
0
0
0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
0
|  |  | 0 |  | 0
| Soll | 39 |  | 36
| Haben |  | 40
Pictures in about
Error Messages Verbessern

## 20
[7 empty] | Sprint | 20
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2021-03-12
|  |  | 0 |  | 0 |  | Bis | 2021-03-26
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
| Added Profile Button and context menu | 4 | 4 | 4 | 0 | Engleder
| Landing Page - Browser Compatibility Fixes (gap, flex... | 10 | 10 | 10 | 0 | Engleder
| Profile View | 4 | 4 | 4 | 0 | Quoc
| Landing Page Navbar | 6 | 6 | 6 | 0 | Quoc
| Guides and Guide Creation - Landing Page Integration | 3 | 3 | 3 | 0 | Wirth
| Profile View Bugs | 4 | 4 | 4 | 0 | Wirth
| Backend Refactor | 3 | 3 | 3 | 0 | Leeb
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
0
0
0
0
0
0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
0
|  |  | 0 |  | 0
| Soll | 34 |  | 34
| Haben |  | 34

## 21
[7 empty] | Sprint | 21
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2021-03-26
[7 empty] | Bis | 2021-04-09
| Guide Sharing | 6 | 6 | 6 | 0 | Engleder
| Profile View fixing | 5 | 5 | 5 | 0 | Engleder
|  |  | 0 |  | 0
| Project Introduction Video Recording 1 | 2 | 2 | 2 | 0 | Engleder
| Project Introduction Video Recording 1 | 2 | 2 | 2 | 0 | Leeb
| Project Introduction Video Recording 1 | 2 | 2 | 2 | 0 | Quoc
| Project Introduction Video Recording 1 | 2 | 2 | 2 | 0 | Wirth
|  |  | 0 |  | 0
| Project Introduction Video Recording 2 | 2 | 2 | 2 | 0 | Engleder
| Project Introduction Video Recording 2 | 2 | 2 | 2 | 0 | Leeb
| Project Introduction Video Recording 2 | 2 | 2 | 2 | 0 | Quoc
| Project Introduction Video Recording 2 | 2 | 2 | 2 | 0 | Wirth
0
| Video Production (1 & 2) | 4 | 4 | 4 | 0 | Engleder
0
| Slides Improvement |  | 0 |  | 0
| Meeting with Prof Bauer | 8 | 8 | 8 | 0 | Engleder, Quoc, Wirth, Leeb
0
0
| Soll | 39 |  | 39
| Haben |  | 31
Pictures in about
Error Messages Verbessern

## 22
[7 empty] | Sprint | 22
User Story | Task | Origin. Estimate | Curr. Estimate | Effort | Remain | Responsible | Von | 2021-04-09
|  |  | 0 |  | 0 |  | Bis | 2021-04-23
|  |  | 0 |  | 0
| Project Award | 8 | 8 | 8 | 0 | Wirth
| Project Award | 8 | 8 | 8 | 0 | Leeb
| Project Award | 8 | 8 | 8 | 0 | Engleder
| Project Award | 8 | 8 | 8 | 0 | Quoc
|  |  | 0 |  | 0
| Profile View Bug Fix | 3 | 3 | 3 | 0 | Wirth
| Geocode Search | 3 | 3 | 3 | 0 | Engleder
| Pending Bug | 1 | 1 | 1 | 0 | Wirth
|  |  | 0 |  | 0
| Recorded & Produced Hauptplatz Demo | 4 | 4 | 4 | 0 | Engleder
|  |  | 0 |  | 0
0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
0
0
0
0
0
0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
0
|  |  | 0 |  | 0
| Soll | 43 |  | 43
| Haben |  | 43
Pictures in about
Error Messages Verbessern