## Tabelle1
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
54 | 0 | 1 | 0
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2020-01-27 | 18 |  | 0 | 20 | 54 | 0 | 0 | 0 | 54 | 0
2020-02-03 | 18 |  | 0 | 15 | 54 | 0 | 0 | 20 | 54 | 0
2020-02-10 | 18 |  | 0 | 20 | 54 | 0 | 0 | 35 | 54 | 0
2020-02-17 | 18 |  | 2 | 20 | 54 | 0 | 2 | 55 | 52 | 0.026667
2020-02-24 | 18 |  | 2 | 20 | 52 | 2 | 4 | 75 | 50 | 0.042105
2020-03-02 | 18 |  | 5 | 20 | 50 | 4 | 9 | 95 | 45 | 0.078261
2020-03-09 | 18 |  |  |  | 45 | 9 | 9 | 115 | 43.5913 | 0.078261
2020-03-16 | 18 |  |  |  | 43.5913 | 9 | 9 | 115 | 42.1826 | 0.078261
2020-03-23 | 18 |  |  |  | 42.1826 | 9 | 9 | 115 | 40.7739 | 0.078261
2020-03-30 | 18 |  |  |  | 40.7739 | 9 | 9 | 115 | 39.3652 | 0.078261
2020-04-06 | 0 |  |  |  | 39.3652 | 9 | 9 | 115 | 39.3652 | 0.078261
2020-04-13 | 0 |  |  |  | 39.3652 | 9 | 9 | 115 | 39.3652 | 0.078261
2020-04-20 | 0 |  |  |  | 39.3652 | 9 | 9 | 115 | 39.3652 | 0.078261
2020-04-27 | 0 |  |  |  | 39.3652 | 9 | 9 | 115 | 39.3652 | 0.078261
2020-05-04 | 0 |  |  |  | 39.3652 | 9 | 9 | 115 | 39.3652 | 0.078261
2020-05-11 | 0 |  |  |  | 39.3652 | 9 | 9 | 115 | 39.3652 | 0.078261
2020-05-18 | 0 |  |  |  | 39.3652 | 9 | 9 | 115 | 39.3652 | 0.078261
2020-05-25 | 0 |  |  |  | 39.3652 | 9 | 9 | 115 | 39.3652 | 0.078261
2020-06-01 | 50 |  |  |  | 39.3652 | 9 | 9 | 115 | 35.4522 | 0.078261
2020-06-08 | 50 |  |  |  | 35.4522 | 9 | 9 | 115 | 31.5391 | 0.078261
2020-06-15 | 50 |  |  |  | 31.5391 | 9 | 9 | 115 | 27.6261 | 0.078261
2020-06-22 | 20 |  |  |  | 27.6261 | 9 | 9 | 115 | 26.0609 | 0.078261
2020-06-29 | 20 |  |  |  | 26.0609 | 9 | 9 | 115 | 24.4957 | 0.078261
2020-07-06 | 20 |  |  |  | 24.4957 | 9 | 9 | 115 | 22.9304 | 0.078261
2020-07-13 | 20 |  |  |  | 22.9304 | 9 | 9 | 115 | 21.3652 | 0.078261
2020-07-20 | 20 |  |  |  | 21.3652 | 9 | 9 | 115 | 19.8 | 0.078261
2020-07-27 | 20 |  |  |  | 19.8 | 9 | 9 | 115 | 18.2348 | 0.078261
2020-08-03 | 20 |  |  |  | 18.2348 | 9 | 9 | 115 | 16.6696 | 0.078261
2020-08-10 | 20 |  |  |  | 16.6696 | 9 | 9 | 115 | 15.1043 | 0.078261
2020-08-17 | 20 |  |  |  | 15.1043 | 9 | 9 | 115 | 13.5391 | 0.078261
2020-08-24 | 20 |  |  |  | 13.5391 | 9 | 9 | 115 | 11.9739 | 0.078261
2020-08-31 | 20 |  |  |  | 11.9739 | 9 | 9 | 115 | 10.4087 | 0.078261
2020-09-07 | 20 |  |  |  | 10.4087 | 9 | 9 | 115 | 8.8435 | 0.078261
2020-09-14 | 20 |  |  |  | 8.8435 | 9 | 9 | 115 | 7.2783 | 0.078261
2020-09-21 | 20 |  |  |  | 7.2783 | 9 | 9 | 115 | 5.713 | 0.078261
2020-09-28 | 20 |  |  |  | 5.713 | 9 | 9 | 115 | 4.1478 | 0.078261
2020-10-05 | 20 |  |  |  | 4.1478 | 9 | 9 | 115 | 2.5826 | 0.078261
2020-10-12 | 20 |  |  |  | 2.5826 | 9 | 9 | 115 | 1.0174 | 0.078261
2020-10-19 | 20 |  |  |  | 1.0174 | 9 | 9 | 115 | 0 | 0.078261
2020-10-26 | 20 |  |  |  | 0 | 9 | 9 | 115 | 0 | 0.078261
2020-11-02 | 20 |  |  |  | 0 | 9 | 9 | 115 | 0 | 0.078261
2020-11-09 | 20 |  |  |  | 0 | 9 | 9 | 115 | 0 | 0.078261
2020-11-16 | 20 |  |  |  | 0 | 9 | 9 | 115 | 0 | 0.078261
2020-11-23 | 20 |  |  |  | 0 | 9 | 9 | 115 | 0 | 0.078261
2020-11-30 | 20 |  |  |  | 0 | 9 | 9 | 115 | 0 | 0.078261
2020-12-07 | 20 |  |  |  | 0 | 9 | 9 | 115 | 0 | 0.078261
| 410 |  | 1.5 | 19.1667
Formulas:
Open Story Points = [Open Story Points, row above]+7