## Sheet1
ID | Prio | EPIC | User Story Name | User Story | Definition of Done | S-Pts. | Done
CAG01 |  | Choose an audio guide | Explorer View | As a user I want to view all audio guides in my vicinity and choose one of them. | • Explorer View with Guides with their Photos and Short Information (server mock data) * Data comes from DB (geo location, name, tags????). Audio info is missing * Information Page, when cklicking on the guide * Sort and filter guides (rating, tags, listenings, popularity (mock data)), | 5 | ✔
UMA01 |  | User Management | Registration | As a user i want to be able to sign up and consequently have a valid user account | * Register with Username E-mail and password(2* zum confirm) (Button to confirm) * check if email has a correct syntax * Sending Confirmation mail with Confirmation Link * Directly Logging in *Waiting for confirmation email? | 2 | ✔
UMA02 |  | User Management | Login | As a user i want to log in | • Login View (email/ password) * Keep Logged in • Authentication (Firebase) * Send User to Explorer View (later to Map View) | 2 | ✔
UMA03 |  | User Management | Secure Data Transfer | As a user i want that my Login Data is not visible for any other person | * Verschlüsselter Datentransfer * JWT für weitere Kommunikation | 2 | ✔
UMA04 |  | User Management | Forgot Password | As a user I want to be able to reset my password | * Show Dialog with email input * Send Firebase reset emai | 1 | ✔
GMA01 |  | Guide Management | Create Guide | As a user I want to be able to create my own guide. | • Guides with his information are added to the db * Guide create view * Test Porting to a Website (Desktop) | 2 | ✔ |  | 18
ROR01 |  | Rate or report guides | Rate | As a user I want to rate or report guides, that i listened to. | * Sterne für Ratings * In Datenbank gespiechert * Bei der GUide INfomration Page | 3 | ✔ |  | 129
PRO01 |  | Profile View |  | As a user i want a overview of my profile | * show all guides of user (desktop version) * show account information of the user * show profile image | 1 | ✔
GMA02 |  | Guide Management | Manage Tracks | As a user I want to edit, order and remove tracks from my own guides. | • User can remove, change order, or upload tracks • The changes are persisted * Handling upload while internet connection cancels * Select guide start (Nearest track - first track) | 2 | ✔
SPI01 |  | Spikes | Beacon Api |  | * Beschäftigung mit den Beacons und wie man sie einsetzten kann | 2 | ✔
UTL01 |  | Utils | Refactoring | We want to refactor some parts | * MongoDB as DB * Redesigned Architecture of the Server * Code Refactoring on Frontend | 2 | ✔
UTL03 |  | Utils | Deployment |  | * Docker Images laufen am Server * Automatisches Deployment, wenn auf master gepusht wird? (CI/CD) | 5 | ✔
GMA06 |  | Guide Management | Geo Location Tagging | As a user i want to manage the tagging of the tracks of my guide. | * Geo Location auswahl beim Track hinzufügen am CLient * Geo Location speicherung bei den tracks am Server | 1 | ✔
SET04 |  | Settings | Background Mode | As a user I still want to listen to a guide, without having to look at my phone and keep the app open. | * Playing Audio works while app isn't open or phone is on standby * If a new track is avalaible, this specific track is played * Informs user that the app is currently running in the background | 5 | ✔
LAG01 |  | Listen to audio guides |  | As a user I want to be able to stream, pause and autoplay audio tracks | * Streaming * minimal lag while pausing * UI like musicplayer * App zu gemacht, trotzdem weiterspielen ?!? * Skip Track * Track Controller on Map View | 3 | ✔
UTL02 |  | Utils | Guides for Tadeot | Upload our tracks | * Collect ideas for the position and the content of the tracks * The tracks are recorded * The Tadeot Guide is created and the tracks are added to the guide | 3 | ✔
UTL03 |  | Utils | Image Video for Tadeot | The School wants an image video for presenting it during Tadeot | * Video with information about architecture adn demo is ready * Video is sent to Bauer or Schröder | 1 | ✔
CAG02 |  | Choose an audio guide | Guide Map UI | As a user I want to view the Guide-Map. | * Display Guides as pins on google maps View (database mock data) * No performance issues when navigating * Display radi (radien) of tracks of guides on map (mock data) * Give info upon click on pin (mock data) | 6 | ✔ | 1
CAG03 |  | Choose an audio guide | Display Radi |  | * Display radi (radien) of tracks of guides on map (mock data) | 2 | ✔
GMA09 |  | Guide Management (Hidden Tracks) | Hide tracks from map | As a user i want to be able to create guides with hidden tracks which are not visible on the map. (Scavenger hunt, Geocaching) | * Toggle the visibility through Track Management page * Track is not shown on map * When in the vicinity of track, track is still played * Track is not shown in track list. | 1 | ✔
GMA10 |  | Guide Management (Share Guide) | Share Guides | As a user i want to be able to share my favorite guides with friends and family. | * Everyone can share guides * Share guide through unique link * Share guide through messengers and social media platforms | 2 | ✔
GMA08 |  | Guide Management (Make Guide Private) | Private Guides | As a user i want to have to possibility to make my guide private and therefore not display it publicly on the guideo map or explorer view. | * Guide is marked as private * It is not visible through the explorer view * It also does not show up on the map * Guide is still accessible through the creator's guide management page * Guide is accessible through a link | 1 | ✔
GMA03 |  | Guide Management (Disable/Delete own Guides) | Delete Guide | As a user i want to have to possibility to delete my created guides | * changes are persisted * All tracks only associated with this guide will be deleted aswell | 2 | ✔ | 6
UTL04 |  | Utils | Improve Tadeot Tracks |  |  | 3 | ✔
SET03 |  | Settings | Dark and Light mode | As a user I want to customize my UI and other features. | • Dark/Light mode | 1 | ✔ |  | x
SET01 |  | Settings | Autoplay | As a user I want to setup the app according to my preferences. | • Autoplay • Easy navigation to settings | 1 | ✔
LAP01 |  | Landing Page | Create Landing Page | As a user i want to get information how to use the app and what the app does, and what i should consider | * Landing page with information for the app * Provides a download link for the app * Fancy/catchy looking web page | 3 | ✔
PRO02 |  | Profile View | Edit Profile View | As a user i want to manage my profile and have the possibility to change my account settings | • Basic Account Settings (change profile picture) * Change Name (Not Username!) * User Description | 3 | ✔
UTL05 |  | Utils | Project Award Preperation |  | * Creating Presentation (slides, videos, ...) * Presentation training | 5 | ✔
GMA07 | 1 | Guide Managment | QR Code Mapping | As a indoor provider, I want also to have a qr-mapping possibility (e.g. museums, events, ...) | * QR-Code Scanning on the Frontend * QR-Code Generation? | 3 | ✖
Sum | [5 empty] | 72