## Tabelle1
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
36 | 0 | 1 | 0
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2020-02-24 | 30 |  | 0 | 32 | 36 | 0 | 0 | 0 | 36 | 0
2020-03-09 | 23 |  | 5 | 17 | 36 | 0 | 5 | 32 | 31 | 0.10204
2020-03-23 | 30 |  | 0 | 27 | 31 | 5 | 5 | 49 | 31 | 0.065789
2020-04-06 | 0 |  | 0 | 0 | 31 | 5 | 5 | 76 | 31 | 0.065789
2020-04-20 | 20 |  | 4 | 15.5 | 31 | 5 | 9 | 76 | 27 | 0.098361
2020-05-04 | 30 |  | 0 | 16.5 | 27 | 9 | 9 | 91.5 | 27 | 0.083333
2020-05-18 | 30 |  | 0 | 29 | 27 | 9 | 9 | 108 | 27 | 0.065693
2020-06-01 | 30 |  | 5 | 33 | 27 | 9 | 14 | 137 | 22 | 0.082353
2020-06-15 | 30 | 3 | 3 | 14 | 25 | 14 | 17 | 170 | 22 | 0.092391 | Report wurde von Rate und Report abgespallten
2020-06-29 | 30 |  | 0 | 0 | 22 | 17 | 17 | 184 | 22 | 0.092391
2020-07-13 | 0 |  | 0 | 0 | 22 | 17 | 17 | 184 | 22 | 0.092391
2020-07-27 | 0 |  | 0 | 0 | 22 | 17 | 17 | 184 | 22 | 0.092391
2020-08-10 | 0 |  | 0 | 0 | 22 | 17 | 17 | 184 | 22 | 0.092391
2020-08-24 | 0 |  | 0 | 0 | 22 | 17 | 17 | 184 | 22 | 0.092391
2020-09-18 | 20 | 2 | 0 | 0 | 24 | 17 | 17 | 184 | 24 | 0.092391 | Refactoring wurde hunzugefügt
2020-10-02 | 30 | 2 | 0 | 20 | 26 | 17 | 17 | 184 | 26 | 0.083333 | Spike Beacon Api hinzugefügt
2020-10-16 | 30 |  | 4 | 16 | 26 | 17 | 21 | 204 | 22 | 0.095455
2020-11-06 | 30 | 5 | 2 | 20 | 27 | 21 | 23 | 220 | 25 | 0.095833 | 3 Wochen sprint wegen 1 Woche Herbstferien
2020-11-20 | 30 | -2 | 3 | 29 | 23 | 23 | 26 | 240 | 20 | 0.096654 | Streamin -2; Deployment + 1
2020-12-04 | 30 | 1 | 3 | 60 | 21 | 26 | 29 | 269 | 18 | 0.088146 | added Image Video for Tadeot
2020-12-18 | 30 |  | 4 | 40 | 18 | 29 | 33 | 329 | 14 | 0.089431
2021-01-08 | 10 |  | 6 | 15 | 14 | 33 | 39 | 369 | 8 | 0.10156 | längerer Sprint wegen Weihnachtsferien
2021-01-22 | 30 |  | 4 | 12 | 8 | 39 | 43 | 384 | 4 | 0.10859
2021-02-05 | 30 | 3 | 1 | 17 | 7 | 43 | 44 | 396 | 6 | 0.10654
2021-02-26 | 30 |  | 0 | 20 | 6 | 44 | 44 | 413 | 6 | 0.10162 | länger wegen Weihnachtsferien
2021-03-12 | 30 | 6 | 3 | 30 | 12 | 44 | 47 | 433 | 9 | 0.10151
2021-03-26 | 30 | 7 | 5 | 30 | 16 | 47 | 52 | 463 | 11 | 0.10548
2021-04-09 | 30 |  | 8 | 25 | 11 | 52 | 60 | 493 | 3 | 0.11583 | Project Award
2021-04-23 | 30 |  |  |  | 3 | 60 | 60 | 518 | 0 | 0.11583 | <--
2021-05-07 | 30 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
2021-05-21 | 30 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
2021-06-04 | 30 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
2021-06-18 | 30 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
2021-07-02 | 0 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
2021-07-16 | 0 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
2021-07-30 | 0 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
2021-08-13 | 0 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
2021-08-27 | 0 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
2021-09-10 | 0 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
2021-09-24 | 0 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
2021-10-08 | 0 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
2021-10-22 | 0 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
2021-11-05 | 0 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
2021-11-19 | 0 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
2021-12-03 | 0 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
2021-12-17 | 0 |  |  |  | 0 | 60 | 60 | 518 | 0 | 0.11583
| 553 |  | 2.1429 | 18.5
Formulas:
Open Story Points = [Open Story Points, row above]+14