## Tabelle1
Initial
Open Story Points | Accomplished SP till now | Hours invested so far | Velocity so far
59 | 0 | 1 | 0
Product Burndown
Sprint | Planned Hours | SP change due to plan change | Accomplished story points in current sprint | Actual Hours | Open Story Points at Begin | Totally Accompl. SP at Begin | Actually accomplished SP at end. | Actual Hours so far at Begin | Open Story Points at End | Velocity (stpts / hour)
2020-02-24 | 30 |  | 0 | 32 | 59 | 0 | 0 | 0 | 59 | 0
2020-03-09 | 23 |  | 5 | 17 | 59 | 0 | 5 | 32 | 54 | 0.10204
2020-03-23 | 30 |  | 0 | 27 | 54 | 5 | 5 | 49 | 54 | 0.065789
2020-04-06 | 0 |  | 0 | 0 | 54 | 5 | 5 | 76 | 54 | 0.065789
2020-04-20 | 20 |  | 4 | 15.5 | 54 | 5 | 9 | 76 | 50 | 0.098361
2020-05-04 | 30 |  | 0 | 16.5 | 50 | 9 | 9 | 91.5 | 50 | 0.083333
2020-05-18 | 30 |  | 0 | 29 | 50 | 9 | 9 | 108 | 50 | 0.065693
2020-06-01 | 30 |  | 5 | 33 | 50 | 9 | 14 | 137 | 45 | 0.082353
2020-06-15 | 30 | 3 | 3 | 14 | 48 | 14 | 17 | 170 | 45 | 0.092391 | Report wurde von Rate und Report abgespallten
2020-06-29 | 30 |  | 0 | 0 | 45 | 17 | 17 | 184 | 45 | 0.092391
2020-07-13 | 0 |  | 0 | 0 | 45 | 17 | 17 | 184 | 45 | 0.092391
2020-07-27 | 0 |  | 0 | 0 | 45 | 17 | 17 | 184 | 45 | 0.092391
2020-08-10 | 0 |  | 0 | 0 | 45 | 17 | 17 | 184 | 45 | 0.092391
2020-08-24 | 0 |  | 0 | 0 | 45 | 17 | 17 | 184 | 45 | 0.092391
2020-09-18 | 20 | 2 | 0 | 0 | 47 | 17 | 17 | 184 | 47 | 0.092391 | Refactoring wurde hunzugefügt
2020-10-02 | 30 | 2 | 0 | 20 | 49 | 17 | 17 | 184 | 49 | 0.083333 | Spike Beacon Api hinzugefügt
2020-10-16 | 30 |  |  |  | 49 | 17 | 17 | 204 | 46.5 | 0.083333
2020-10-30 | 30 |  |  |  | 46.5 | 17 | 17 | 204 | 44 | 0.083333
2020-11-13 | 30 |  |  |  | 44 | 17 | 17 | 204 | 41.5 | 0.083333
2020-11-27 | 30 |  |  |  | 41.5 | 17 | 17 | 204 | 39 | 0.083333
2020-12-11 | 30 |  |  |  | 39 | 17 | 17 | 204 | 36.5 | 0.083333
2020-12-25 | 0 |  |  |  | 36.5 | 17 | 17 | 204 | 36.5 | 0.083333
2021-01-08 | 30 |  |  |  | 36.5 | 17 | 17 | 204 | 34 | 0.083333
2021-01-22 | 30 |  |  |  | 34 | 17 | 17 | 204 | 31.5 | 0.083333
2021-02-05 | 30 |  |  |  | 31.5 | 17 | 17 | 204 | 29 | 0.083333
2021-02-19 | 30 |  |  |  | 29 | 17 | 17 | 204 | 26.5 | 0.083333
2021-03-05 | 30 |  |  |  | 26.5 | 17 | 17 | 204 | 24 | 0.083333
2021-03-19 | 30 |  |  |  | 24 | 17 | 17 | 204 | 21.5 | 0.083333
2021-04-02 | 30 |  |  |  | 21.5 | 17 | 17 | 204 | 19 | 0.083333
2021-04-16 | 30 |  |  |  | 19 | 17 | 17 | 204 | 16.5 | 0.083333
2021-04-30 | 30 |  |  |  | 16.5 | 17 | 17 | 204 | 14 | 0.083333
2021-05-14 | 30 |  |  |  | 14 | 17 | 17 | 204 | 11.5 | 0.083333
2021-05-28 | 0 |  |  |  | 11.5 | 17 | 17 | 204 | 11.5 | 0.083333
2021-06-11 | 0 |  |  |  | 11.5 | 17 | 17 | 204 | 11.5 | 0.083333
2021-06-25 | 0 |  |  |  | 11.5 | 17 | 17 | 204 | 11.5 | 0.083333
2021-07-09 | 0 |  |  |  | 11.5 | 17 | 17 | 204 | 11.5 | 0.083333
2021-07-23 | 0 |  |  |  | 11.5 | 17 | 17 | 204 | 11.5 | 0.083333
2021-08-06 | 0 |  |  |  | 11.5 | 17 | 17 | 204 | 11.5 | 0.083333
2021-08-20 | 0 |  |  |  | 11.5 | 17 | 17 | 204 | 11.5 | 0.083333
2021-09-03 | 0 |  |  |  | 11.5 | 17 | 17 | 204 | 11.5 | 0.083333
2021-09-17 | 0 |  |  |  | 11.5 | 17 | 17 | 204 | 11.5 | 0.083333
2021-10-01 | 0 |  |  |  | 11.5 | 17 | 17 | 204 | 11.5 | 0.083333
2021-10-15 | 0 |  |  |  | 11.5 | 17 | 17 | 204 | 11.5 | 0.083333
2021-10-29 | 0 |  |  |  | 11.5 | 17 | 17 | 204 | 11.5 | 0.083333
2021-11-12 | 0 |  |  |  | 11.5 | 17 | 17 | 204 | 11.5 | 0.083333
2021-11-26 | 0 |  |  |  | 11.5 | 17 | 17 | 204 | 11.5 | 0.083333
| 543 |  | 1.0625 | 12.75
Formulas:
Open Story Points = [Open Story Points, row above]+14